**Notice of Contract Change Order/Amendment**

Contract Title: District 5 Lighting Repair 2021-1

IDOT Reference Number: 70F16A1

Source Selection Method (Change Order or Amendment): Amendment

Contract Type: Construction Support

Description of change: This amendment request is to add $267,942.50 in additional funding to the contract to fund the purchase of material necessary to do the repairs which are included in the original scope of the contract and to extend the completion date to June 30, 2022.

The completion date will be  extended,  shortened or  remain the same.

Original completion date: 12/31/2021

Revised completion date: 6/30/2022

Method of determining compensation (e.g., hourly rate, fixed fee, etc.) will  stay the same or  change as follows:

The cost will be  increased,  decreased or  remain the same.

Original cost: $352,057.50

Amount of change: $267,942.50

Revised cost: $620,000.00

The supplies or services to be provided will  stay the same or  be changed as follows:

Subcontractors are being  added,  deleted, or  remain the same?

Subcontractor Name:

added  deleted

Amount to be paid:

Address:

Description of work: