**Notice of Contract Change Order/Amendment**

Contract Title: District 5 Lighting Repair 2021-1

IDOT Reference Number: 70F16A1

Source Selection Method (Change Order or Amendment): Amendment

Contract Type: Construction Support

Description of change: This amendment request is to add $267,942.50 in additional funding to the contract to fund the purchase of material necessary to do the repairs which are included in the original scope of the contract and to extend the completion date to June 30, 2022.

The completion date will be [x]  extended, [ ]  shortened or [ ]  remain the same.

 Original completion date: 12/31/2021

 Revised completion date: 6/30/2022

Method of determining compensation (e.g., hourly rate, fixed fee, etc.) will [x]  stay the same or [ ]  change as follows:

The cost will be [x]  increased, [ ]  decreased or [ ]  remain the same.

Original cost: $352,057.50

 Amount of change: $267,942.50

 Revised cost: $620,000.00

The supplies or services to be provided will [x]  stay the same or [ ]  be changed as follows:

Subcontractors are being [ ]  added, [ ]  deleted, or [x]  remain the same?

Subcontractor Name:

[ ]  added [ ]  deleted

Amount to be paid:

Address:

Description of work: