**Notice of Contract Change Order/Amendment**

Contract Title: Corrugated Metal Culverts

IDOT Reference Number: 2020-09R1

Source Selection Method (Change Order or Amendment): Amendment #1

Contract Type: Construction Support

Description of change: Amendment #1 is to increase the cost of the materials per Section 2.3 of the current contract.

The completion date will be  extended,  shortened or  remain the same.

Original completion date:

Revised completion date:

Method of determining compensation (e.g., hourly rate, fixed fee, etc.) will  stay the same or  change as follows:

The cost will be  increased,  decreased or  remain the same.

Original cost: $718,818.85

Amount of change: $161,364.60

Revised cost: $880,183.45

The supplies or services to be provided will  stay the same or  be changed as follows:

Subcontractors are being  added,  deleted, or  remain the same?

Subcontractor Name:

added  deleted

Amount to be paid:

Address:

Description of work:

Effective Date of Amendment: Upon Execution